Weekly reports are to be emailed to atbecker@uh.edu by 5:00pm on Tuesdays.  The purpose of a weekly report is to: (1) give you text and images for your papers, thesis, and dissertation, (2) document progress, (3) identify if you are stuck or need resources.

Weekly report

- My Goals from last week

  - Build new SMT platform with open build materials for 1m and 4m

  - Record 1m pulse train experiment video

  - Take photos of new platform

  - Start writing draft of paper

  - Complete TA work

- My Accomplishments this week

- Scored work sheet1 and 2, communicated with student who had confuse or submit wrong file by mistakes.

- Complete 1m experiment platform and take photos for setup

- Record 1m pulse train video

- Complete 4m set up frame, we can not finish because the nylon tubing doesn’t fit with acrylic conduits, we are waiting for lubricant and new conduits.

- Complete abstract and experiment setup(plan)

- My Goals for next week

- Continue writing draft

- Complete 4m mimic MRI environment experiment

- Complete TA work

- What I need Dr. Becker to do:

  - Please send me the course homework and worksheet answer