Weekly report

- My Goals from last week

  - Gather more drop test data – Delayed Until Dart Is Complete To Get All Data At Once

  - Integration of the photon and power source

  - Start on housing part for the photon

- My Accomplishments this week

  - Project 1: Photon/Accelerometer system integration

- Established communication between the user and the Photon microcontroller over Wi-Fi to retrieve data from sensors. Put together one system with the power source and sensor for one dart to start designing a part to house the system.

- Started on the part for the housing of the system—research/design phase

  - Project 2: Cardboard Grid For Magnetic Field Data From a Geophone Magnet

- Made a cardboard Euclidian grid so that Srikanth and I could measure the magnetic field of the geophone sensor at many points on a plane. The grid was 30cm by 15 cm large. We got a lot of data for the radial and axial components of the field but it turns out that we weren’t sure if the Gaussmeter was able to measure these values—and so I believe Srikanth will talk to you about this and the alternative soon.

Figure 1:  Small Grid made to measure the magnetic field of the geophone magnet (shown at the bottom center of grid) at specific points on a plane.

- My Goals for next week

- Housing part for electronics in the dart—really want to focus on this

- Communication between multiple photon’s at once—have started

- Start learning how to use the cellular Electron

  - Meeting with Dr. Becker on Monday May 30th 2016 at 10:00am